## Sheet1
Story | Estimation(days) | Priority
As a client I want to create an account. | 2 | 1
As a client I want to login. | 3 | 1
As a client I want to login with gmail. | 2 | 2
As a client I want to receive email validation. | 1 | 2
As a client I want to edit my account. | 0.5 | 2
As a client I want to filter trains. | 1 | 3
As a client I want to save the train filter. | 1 | 4
As a client I want to filter by date/relevance. | 3 | 3
As a client I want to receive train suggestions. | 3 | 5 | Priority queue 1 - very high 2 - high 3 - medium high 4 - medium low 5 - low 6 - very low
As a client I want to share trains. | 2 | 6
As a client I want to see the train on radar map. | 7 | 4
As a client I want to choose a ticket type. | 1 | 2
As a client I want to see each disscount depending on the ticket type. | 1 | 2
As a client I want to see the train information. | 0.5 | 3
As an admin I want to update pricing rules for the tickets. | 2 | 1
As an admin I want to manage a payment platform. | 5 | 1
As an admin I want to lock or unlock an account. | 1 | 1
As an admin I want to manage user roles. | 3 | 1
As an admin I want to post reference tables | 2 | 1
As an admin I want to manage routes and trains. | 5 | 1
As an information analyst I want to update the timetable. | 1 | 2
As an infotmation analyst I want to notify travelers about any delays. | 4 | 3
As an information analyst I want to update train information. | 1 | 2
As an information analyst I want to update routes. | 2 | 2
As a ticket colector I want to see my daily assigned trains. | 1 | 1
As a ticket colector I want to check each traveler by the app. | 1 | 1
As a ticket colector I want to notify the admin about any problems. | 3 | 3
As an engineer I want to see my daily assigned trains. | 1 | 1
As an engineer I want to see my daily assigned tasks. | 1 | 2
As an engineer I want to update the train status. | 1 | 3